## Dashboard
Machine Learning & Deep Learning Study Plan
[5 empty] | Week | Planned hours
Plan Start | 2026-07-13 |  | Progress KPI | Value | 1 | 24
Plan End | 2026-12-05 |  | Completed days | 0 | 2 | 24
Scheduled Study Days | 126 |  | In-progress days | 0 | 3 | 24
Study Time per Day | 4 hours |  | Overall completion | 0% | 4 | 24
Planned Study Hours | 504 |  | Actual hours logged | 0 | 5 | 24
Buffer Sundays | 21 |  |  |  | 6 | 24
Learning Pace | Slow and practice-first |  |  |  | 7 | 24
[5 empty] | 8 | 24
Daily 4-Hour Method |  |  |  |  | 9 | 24
Block | Minutes | What to do | Rule |  | 10 | 24
1. Learn concept | 80 | Read/watch and make concise notes | Use active recall; do not copy long notes. |  | 11 | 24
2. Guided coding | 95 | Follow a notebook/tutorial once | Type code yourself and add comments. |  | 12 | 24
3. Independent practice | 45 | Solve/modify without looking | Produce the listed daily deliverable. |  | 13 | 24
4. Revision | 20 | Recall yesterday + key formula/idea | Use flashcards or a 5-question self-quiz. |  | 14 | 24
[5 empty] | 15 | 24
How to use this workbook |  |  |  |  | 16 | 24
Every Monday–Saturday row is a 3-hour plan. Update Status and Actual Hours in Daily Plan. Do not schedule anything on Sunday: use it only when you miss a task or need extra time for a hard topic. Complete the listed deliverable before moving on. Revision is intentionally daily and full-module revision is scheduled each week. |  |  |  |  | 17 | 24
[5 empty] | 18 | 24
[5 empty] | 19 | 24
[5 empty] | 20 | 24
[5 empty] | 21 | 24
Chart data helper

## Daily Plan
Date | Day | Week | Module | Topic / Chapter Focus | Learning Objective | Theory (min) | Guided Learning / Coding (min) | Independent Practice (min) | Revision (min) | Total (min) | Daily Deliverable | Status | Actual Hours | Notes | Completion %
2026-08-12 | Wednesday | 3 | 3. Regression Models I | Decision trees for regression | Understand splits, leaf predictions and tree depth. | 60 | 45 | 45 | 30 | 180 | Train a regression tree and visualize decision rules. | Not Started |  |  | 0%
2026-08-13 | Thursday | 3 | 3. Regression Models I | Random forests for regression | Understand bagging, feature randomness and averaging. | 60 | 45 | 45 | 30 | 180 | Compare one decision tree vs random forest. | Not Started |  |  | 0%
2026-08-14 | Friday | 3 | 3. Regression Models I | Gradient-boosting machines | Explain sequential error correction, learning rate and trees. | 60 | 45 | 45 | 30 | 180 | Train a gradient boosting regressor and tune learning rate. | Not Started |  |  | 0%
2026-08-15 | Saturday | 3 | 3. Regression Models I | Regression model comparison + weekly review | Select models using consistent validation. | 60 | 45 | 45 | 30 | 180 | Create a comparison table for Linear/Tree/RF/GBM. | Not Started |  |  | 0%
2026-08-17 | Monday | 4 | 4. Regression Models II & Taxi Fare Project | Support Vector Regression (SVR) | Understand epsilon tube, support vectors and kernels. | 60 | 45 | 45 | 30 | 180 | Fit linear and RBF SVR on a small dataset. | Not Started |  |  | 0%
2026-08-18 | Tuesday | 4 | 4. Regression Models II & Taxi Fare Project | Regression metrics: MAE, MSE, RMSE, R² | Match metric to business cost. | 60 | 45 | 45 | 30 | 180 | Calculate metrics manually for 5 predictions. | Not Started |  |  | 0%
2026-08-19 | Wednesday | 4 | 4. Regression Models II & Taxi Fare Project | Advanced regression diagnostics | Interpret residual plots, outliers and systematic errors. | 60 | 45 | 45 | 30 | 180 | Diagnose 3 supplied regression failure scenarios. | Not Started |  |  | 0%
2026-08-20 | Thursday | 5 | 5. Classification Models I | Logistic regression intuition | Understand probabilities, logits, sigmoid and decision boundary. | 60 | 45 | 45 | 30 | 180 | Compute sigmoid probabilities for 5 logit values. | Not Started |  |  | 0%
2026-08-21 | Friday | 5 | 5. Classification Models I | Classification metrics: accuracy, precision, recall, F1 | Choose metrics based on false-positive/false-negative cost. | 60 | 45 | 45 | 30 | 180 | Build a metric-selection cheat sheet. | Not Started |  |  | 0%
2026-08-22 | Saturday | 5 | 5. Classification Models I | Confusion matrix, ROC-AUC and PR-AUC | Interpret threshold-dependent and ranking metrics. | 60 | 45 | 45 | 30 | 180 | Plot ROC and precision–recall curves. | Not Started |  |  | 0%
2026-08-24 | Monday | 5 | 5. Classification Models I | Categorical data and encoding | Use one-hot encoding safely; avoid dummy-variable pitfalls. | 60 | 45 | 45 | 30 | 180 | Encode categorical columns using a pipeline. | Not Started |  |  | 0%
2026-08-25 | Tuesday | 5 | 5. Classification Models I | Binary classification workflow | Build baseline, threshold and evaluation workflow. | 60 | 45 | 45 | 30 | 180 | Train logistic regression on a binary dataset. | Not Started |  |  | 0%
2026-08-26 | Wednesday | 5 | 5. Classification Models I | Classification revision + quiz | Explain every core metric in plain language. | 60 | 45 | 45 | 30 | 180 | 20-question self-test plus corrections. | Not Started |  |  | 0%
2026-08-27 | Thursday | 6 | 6. Classification Models II | Titanic project: EDA and feature engineering | Prepare mixed-type data for classification. | 60 | 45 | 45 | 30 | 180 | Build preprocessing pipeline for Titanic data. | Not Started |  |  | 0%
2026-08-28 | Friday | 6 | 6. Classification Models II | Titanic project: model and evaluation | Compare logistic regression and tree-based classifier. | 60 | 45 | 45 | 30 | 180 | Create confusion matrix and metric report. | Not Started |  |  | 0%
2026-08-29 | Saturday | 6 | 6. Classification Models II | Class imbalance and credit-card fraud | Understand imbalance, class weights, resampling and thresholding. | 60 | 45 | 45 | 30 | 180 | Show why accuracy is misleading on imbalanced data. | Not Started |  |  | 0%
2026-08-31 | Monday | 6 | 6. Classification Models II | Fraud detection practice | Evaluate with precision-recall, F1 and recall at a threshold. | 60 | 45 | 45 | 30 | 180 | Train a class-weighted model and compare results. | Not Started |  |  | 0%
2026-09-01 | Tuesday | 6 | 6. Classification Models II | Multiclass classification | Understand one-vs-rest, softmax and macro/micro metrics. | 60 | 45 | 45 | 30 | 180 | Train an Iris/digits multiclass model. | Not Started |  |  | 0%
2026-09-02 | Wednesday | 6 | 6. Classification Models II | Digit-recognition project + review | Build and explain a multiclass pipeline. | 60 | 45 | 45 | 30 | 180 | Complete digits classifier and revise Weeks 5–6. | Not Started |  |  | 0%
2026-09-03 | Thursday | 7 | 7. Text Classification | Text preparation | Tokenization, lowercasing, stop words, stemming/lemmatization. | 60 | 45 | 45 | 30 | 180 | Clean 30 sample reviews and compare raw vs cleaned text. | Not Started |  |  | 0%
2026-09-04 | Friday | 7 | 7. Text Classification | Bag of Words and TF-IDF | Convert text to sparse numeric features. | 60 | 45 | 45 | 30 | 180 | Build CountVectorizer and TfidfVectorizer representations. | Not Started |  |  | 0%
2026-09-05 | Saturday | 7 | 7. Text Classification | Sentiment analysis workflow | Frame sentiment task and evaluate it. | 60 | 45 | 45 | 30 | 180 | Train baseline sentiment classifier. | Not Started |  |  | 0%
2026-09-07 | Monday | 7 | 7. Text Classification | Naive Bayes intuition | Explain conditional probability and independence assumption. | 60 | 45 | 45 | 30 | 180 | Calculate a small Naive Bayes example manually. | Not Started |  |  | 0%
2026-09-08 | Tuesday | 7 | 7. Text Classification | Spam filtering | Build spam/ham classifier and inspect errors. | 60 | 45 | 45 | 30 | 180 | Create a Naive Bayes spam filter notebook. | Not Started |  |  | 0%
2026-09-09 | Wednesday | 7 | 7. Text Classification | Text-classification review | Compare preprocessing/vectorization/model choices. | 60 | 45 | 45 | 30 | 180 | Write error analysis for 10 wrong predictions. | Not Started |  |  | 0%
2026-09-10 | Thursday | 8 | 8. Recommenders & SVM Introduction | Recommender systems overview | Differentiate content-based, collaborative and hybrid approaches. | 60 | 45 | 45 | 30 | 180 | Map 6 product examples to recommender type. | Not Started |  |  | 0%
2026-09-11 | Friday | 8 | 8. Recommenders & SVM Introduction | Cosine similarity | Understand vector angle similarity. | 60 | 45 | 45 | 30 | 180 | Compute cosine similarity manually and in Python. | Not Started |  |  | 0%
2026-09-12 | Saturday | 8 | 8. Recommenders & SVM Introduction | Movie recommendation system | Build content-based recommendations. | 60 | 45 | 45 | 30 | 180 | Recommend 5 similar movies using TF-IDF + cosine similarity. | Not Started |  |  | 0%
2026-09-14 | Monday | 8 | 8. Recommenders & SVM Introduction | Recommendation evaluation and limitations | Understand cold start, diversity and popularity bias. | 60 | 45 | 45 | 30 | 180 | Write a mitigation plan for each limitation. | Not Started |  |  | 0%
2026-09-15 | Tuesday | 8 | 8. Recommenders & SVM Introduction | SVM intuition: maximum-margin classifier | Explain margin and support vectors. | 60 | 45 | 45 | 30 | 180 | Draw separating hyperplanes for a tiny 2D dataset. | Not Started |  |  | 0%
2026-09-16 | Wednesday | 8 | 8. Recommenders & SVM Introduction | Bridge practice + revision | Connect text vectors, cosine similarity and SVM. | 60 | 45 | 45 | 30 | 180 | Rebuild movie recommender; revise Weeks 7–8. | Not Started |  |  | 0%
2026-09-17 | Thursday | 9 | 9. Support Vector Machines | How SVM works | Understand hard/soft margin and C parameter. | 60 | 45 | 45 | 30 | 180 | Train linear SVM with three C values. | Not Started |  |  | 0%
2026-09-18 | Friday | 9 | 9. Support Vector Machines | Kernels | Recognize when linear boundaries are insufficient. | 60 | 45 | 45 | 30 | 180 | Visualize linear vs nonlinear decision boundary. | Not Started |  |  | 0%
2026-09-19 | Saturday | 9 | 9. Support Vector Machines | Kernel trick | Explain implicit high-dimensional transformation. | 60 | 45 | 45 | 30 | 180 | Compare linear, polynomial and RBF kernels. | Not Started |  |  | 0%
2026-09-21 | Monday | 9 | 9. Support Vector Machines | Hyperparameter tuning | Tune C, gamma and kernel with cross-validation. | 60 | 45 | 45 | 30 | 180 | Run GridSearchCV for SVM pipeline. | Not Started |  |  | 0%
2026-09-22 | Tuesday | 9 | 9. Support Vector Machines | Data normalization and pipelining | Prevent leakage by scaling inside a pipeline. | 60 | 45 | 45 | 30 | 180 | Build StandardScaler + SVC pipeline. | Not Started |  |  | 0%
2026-09-23 | Wednesday | 9 | 9. Support Vector Machines | Facial-recognition SVM case study + review | Apply SVM workflow to high-dimensional features. | 60 | 45 | 45 | 30 | 180 | Complete a simplified faces/SVM notebook. | Not Started |  |  | 0%
2026-09-24 | Thursday | 10 | 10. Principal Component Analysis | PCA intuition | Understand variance, components and dimensionality reduction. | 60 | 45 | 45 | 30 | 180 | Project simple 2D points onto first component. | Not Started |  |  | 0%
2026-09-25 | Friday | 10 | 10. Principal Component Analysis | PCA mechanics | Understand centering, covariance and eigenvector intuition. | 60 | 45 | 45 | 30 | 180 | Apply PCA to standardized numerical data. | Not Started |  |  | 0%
2026-09-26 | Saturday | 10 | 10. Principal Component Analysis | Choosing components; explained variance | Use scree/explained-variance plots. | 60 | 45 | 45 | 30 | 180 | Choose components for 90%, 95%, 99% variance. | Not Started |  |  | 0%
2026-09-28 | Monday | 10 | 10. Principal Component Analysis | Filtering noise | Use reconstruction to reduce low-variance noise. | 60 | 45 | 45 | 30 | 180 | Compare original/noisy/reconstructed signals. | Not Started |  |  | 0%
2026-09-29 | Tuesday | 10 | 10. Principal Component Analysis | Anonymizing and visualizing high-dimensional data | Understand benefits and limitations of projection. | 60 | 45 | 45 | 30 | 180 | Visualize digits in 2D PCA space. | Not Started |  |  | 0%
2026-09-30 | Wednesday | 10 | 10. Principal Component Analysis | PCA revision + practice | Explain PCA without formulas and with formulas. | 60 | 45 | 45 | 30 | 180 | Build a PCA comparison notebook and self-quiz. | Not Started |  |  | 0%
2026-10-01 | Thursday | 11 | 11. PCA Applications & Operationalization I | PCA for anomaly detection | Use reconstruction error or low-dimensional distance. | 60 | 45 | 45 | 30 | 180 | Detect anomalies in a toy dataset. | Not Started |  |  | 0%
2026-10-02 | Friday | 11 | 11. PCA Applications & Operationalization I | PCA credit-card fraud case study | Frame anomalies and inspect false alarms. | 60 | 45 | 45 | 30 | 180 | Create PCA-based anomaly score pipeline. | Not Started |  |  | 0%
2026-10-03 | Saturday | 11 | 11. PCA Applications & Operationalization I | Bearing-failure prediction case study | Understand multivariate sensor anomaly workflow. | 60 | 45 | 45 | 30 | 180 | Analyze synthetic sensor features with PCA. | Not Started |  |  | 0%
2026-10-05 | Monday | 11 | 11. PCA Applications & Operationalization I | Multivariate anomaly detection | Compare statistical and PCA approaches. | 60 | 45 | 45 | 30 | 180 | Write detection threshold rationale. | Not Started |  |  | 0%
2026-10-06 | Tuesday | 11 | 11. PCA Applications & Operationalization I | Python model client consumption | Load model and serve predictions to a Python caller. | 60 | 45 | 45 | 30 | 180 | Save/load a scikit-learn model with joblib. | Not Started |  |  | 0%
2026-10-07 | Wednesday | 11 | 11. PCA Applications & Operationalization I | Pickle versioning + weekly review | Handle compatibility and metadata. | 60 | 45 | 45 | 30 | 180 | Create model artifact folder with version metadata. | Not Started |  |  | 0%
2026-10-08 | Thursday | 12 | 12. Operationalization II & Deep Learning Intro | Consume model from C# conceptually; ONNX bridge | Understand portability, model formats and trade-offs. | 60 | 45 | 45 | 30 | 180 | Export a simple model to ONNX or document the flow. | Not Started |  |  | 0%
2026-10-09 | Friday | 12 | 12. Operationalization II & Deep Learning Intro | Containerizing an ML model | Understand Dockerfile, API, dependencies and image. | 60 | 45 | 45 | 30 | 180 | Containerize a minimal prediction API or write Dockerfile. | Not Started |  |  | 0%
2026-10-10 | Saturday | 12 | 12. Operationalization II & Deep Learning Intro | ML.NET overview; sentiment analysis | Understand cross-language ML deployment. | 60 | 45 | 45 | 30 | 180 | Recreate sentiment-flow design in notes. | Not Started |  |  | 0%
2026-10-12 | Monday | 12 | 12. Operationalization II & Deep Learning Intro | Excel ML capabilities + operationalization review | Identify business-friendly model consumption paths. | 60 | 45 | 45 | 30 | 180 | Create a deployment decision matrix. | Not Started |  |  | 0%
2026-10-13 | Tuesday | 12 | 12. Operationalization II & Deep Learning Intro | Deep learning fundamentals | Understand neurons, layers, activations and representations. | 60 | 45 | 45 | 30 | 180 | Build a 1-neuron calculation by hand. | Not Started |  |  | 0%
2026-10-14 | Wednesday | 12 | 12. Operationalization II & Deep Learning Intro | Training neural networks | Understand loss, backpropagation, optimizer and epochs. | 60 | 45 | 45 | 30 | 180 | Train a tiny Keras model; revise Week 12. | Not Started |  |  | 0%
2026-10-15 | Thursday | 13 | 13. Neural Networks I | Keras/TensorFlow workflow | Build, compile, fit and evaluate a Sequential model. | 60 | 45 | 45 | 30 | 180 | Train a basic dense network. | Not Started |  |  | 0%
2026-10-16 | Friday | 13 | 13. Neural Networks I | Sizing a neural network | Choose depth/width based on task complexity. | 60 | 45 | 45 | 30 | 180 | Compare small, medium and large architectures. | Not Started |  |  | 0%
2026-10-17 | Saturday | 13 | 13. Neural Networks I | Neural-net regression: taxi fares | Apply dense networks to continuous target. | 60 | 45 | 45 | 30 | 180 | Train NN regression baseline and compare RMSE. | Not Started |  |  | 0%
2026-10-19 | Monday | 13 | 13. Neural Networks I | Binary classification with neural networks | Use sigmoid/BCE and thresholding. | 60 | 45 | 45 | 30 | 180 | Train a binary classifier. | Not Started |  |  | 0%
2026-10-20 | Tuesday | 13 | 13. Neural Networks I | Making predictions; calibration basics | Interpret probabilities and prediction outputs. | 60 | 45 | 45 | 30 | 180 | Inspect 20 predictions and their confidence. | Not Started |  |  | 0%
2026-10-21 | Wednesday | 13 | 13. Neural Networks I | Neural-network review | Explain architecture-to-output mapping. | 60 | 45 | 45 | 30 | 180 | Rebuild a binary NN without looking at notes. | Not Started |  |  | 0%
2026-10-22 | Thursday | 14 | 14. Neural Networks II | NN for credit-card fraud | Handle imbalance in deep learning. | 60 | 45 | 45 | 30 | 180 | Use class weights and PR metrics. | Not Started |  |  | 0%
2026-10-23 | Friday | 14 | 14. Neural Networks II | Multiclass neural networks | Use softmax and sparse/categorical cross-entropy. | 60 | 45 | 45 | 30 | 180 | Train a digits multiclass dense NN. | Not Started |  |  | 0%
2026-10-24 | Saturday | 14 | 14. Neural Networks II | Face-recognition neural-network case study | Understand embeddings and classification heads. | 60 | 45 | 45 | 30 | 180 | Build a conceptual embedding workflow. | Not Started |  |  | 0%
2026-10-26 | Monday | 14 | 14. Neural Networks II | Dropout and regularization | Reduce overfitting in neural networks. | 60 | 45 | 45 | 30 | 180 | Compare training curves with/without dropout. | Not Started |  |  | 0%
2026-10-27 | Tuesday | 14 | 14. Neural Networks II | Saving/loading models | Persist weights, architecture and full model. | 60 | 45 | 45 | 30 | 180 | Save and reload a Keras model. | Not Started |  |  | 0%
2026-10-28 | Wednesday | 14 | 14. Neural Networks II | Keras callbacks + revision | Use EarlyStopping, ModelCheckpoint and ReduceLROnPlateau. | 60 | 45 | 45 | 30 | 180 | Add callbacks to a training notebook. | Not Started |  |  | 0%
2026-10-29 | Thursday | 15 | 15. CNN Foundations | CNN intuition | Understand convolution, filters, feature maps and pooling. | 60 | 45 | 45 | 30 | 180 | Manually apply a tiny convolution kernel. | Not Started |  |  | 0%
2026-10-30 | Friday | 15 | 15. CNN Foundations | Build CNNs with Keras/TensorFlow | Create Conv2D/Pooling/Flatten/Dense pipeline. | 60 | 45 | 45 | 30 | 180 | Train a CNN on a small image dataset. | Not Started |  |  | 0%
2026-10-31 | Saturday | 15 | 15. CNN Foundations | Arctic-wildlife image classification | Prepare image dataset and baseline. | 60 | 45 | 45 | 30 | 180 | Create data pipeline and first CNN. | Not Started |  |  | 0%
2026-11-02 | Monday | 15 | 15. CNN Foundations | Pretrained CNNs | Understand feature extractors and ImageNet transfer. | 60 | 45 | 45 | 30 | 180 | Run inference using pretrained ResNet50V2. | Not Started |  |  | 0%
2026-11-03 | Tuesday | 15 | 15. CNN Foundations | Transfer learning | Freeze/unfreeze layers and fine-tune safely. | 60 | 45 | 45 | 30 | 180 | Compare scratch model vs transfer learning. | Not Started |  |  | 0%
2026-11-04 | Wednesday | 15 | 15. CNN Foundations | CNN revision + practice | Explain complete image-classification pipeline. | 60 | 45 | 45 | 30 | 180 | Document results and errors from wildlife model. | Not Started |  |  | 0%
2026-11-05 | Thursday | 16 | 16. CNN Advanced | Transfer learning for Arctic wildlife | Fine-tune model with appropriate learning rate. | 60 | 45 | 45 | 30 | 180 | Train and evaluate transfer-learning model. | Not Started |  |  | 0%
2026-11-06 | Friday | 16 | 16. CNN Advanced | Data augmentation concepts | Reduce overfitting with realistic transformations. | 60 | 45 | 45 | 30 | 180 | Design augmentation policy for wildlife images. | Not Started |  |  | 0%
2026-11-07 | Saturday | 16 | 16. CNN Advanced | ImageDataGenerator | Implement legacy image augmentation workflow. | 60 | 45 | 45 | 30 | 180 | Train model with ImageDataGenerator. | Not Started |  |  | 0%
2026-11-09 | Monday | 16 | 16. CNN Advanced | Augmentation layers | Use modern in-model augmentation layers. | 60 | 45 | 45 | 30 | 180 | Compare augmentation-layer result with legacy method. | Not Started |  |  | 0%
2026-11-10 | Tuesday | 16 | 16. CNN Advanced | Global pooling | Understand GlobalAveragePooling and parameter reduction. | 60 | 45 | 45 | 30 | 180 | Compare Flatten vs global pooling parameter counts. | Not Started |  |  | 0%
2026-11-11 | Wednesday | 16 | 16. CNN Advanced | Audio classification with CNNs + review | Convert audio to spectrograms and classify. | 60 | 45 | 45 | 30 | 180 | Create mini spectrogram-CNN experiment. | Not Started |  |  | 0%
2026-11-12 | Thursday | 17 | 17. Face Detection & Recognition | Face detection; Viola-Jones | Understand Haar features and cascade concept. | 60 | 45 | 45 | 30 | 180 | Run OpenCV Haar Cascade face detection. | Not Started |  |  | 0%
2026-11-13 | Friday | 17 | 17. Face Detection & Recognition | OpenCV face extraction | Crop and align detected faces. | 60 | 45 | 45 | 30 | 180 | Extract faces from a folder of photos. | Not Started |  |  | 0%
2026-11-14 | Saturday | 17 | 17. Face Detection & Recognition | CNN face detection | Understand modern detector advantages. | 60 | 45 | 45 | 30 | 180 | Compare cascade vs CNN detector conceptually. | Not Started |  |  | 0%
2026-11-16 | Monday | 17 | 17. Face Detection & Recognition | Facial recognition; transfer learning | Learn embeddings and similarity classification. | 60 | 45 | 45 | 30 | 180 | Build a small embedding-based recognition demo. | Not Started |  |  | 0%
2026-11-17 | Tuesday | 17 | 17. Face Detection & Recognition | Task-specific weights; ArcFace | Understand margin-based face embeddings. | 60 | 45 | 45 | 30 | 180 | Explain ArcFace in your own words with diagram. | Not Started |  |  | 0%
2026-11-18 | Wednesday | 17 | 17. Face Detection & Recognition | Unknown faces; open vs closed set + review | Handle rejection/unknown identities. | 60 | 45 | 45 | 30 | 180 | Add unknown thresholding logic to demo. | Not Started |  |  | 0%
2026-11-19 | Thursday | 18 | 18. Object Detection | Object detection framing; R-CNN family | Understand boxes, labels, proposals and IoU. | 60 | 45 | 45 | 30 | 180 | Draw and label 10 bounding-box examples. | Not Started |  |  | 0%
2026-11-20 | Friday | 18 | 18. Object Detection | Mask R-CNN | Differentiate detection from instance segmentation. | 60 | 45 | 45 | 30 | 180 | Compare R-CNN, Faster R-CNN and Mask R-CNN. | Not Started |  |  | 0%
2026-11-21 | Saturday | 18 | 18. Object Detection | YOLO | Understand single-stage detection and speed trade-off. | 60 | 45 | 45 | 30 | 180 | Run pretrained YOLO inference. | Not Started |  |  | 0%
2026-11-23 | Monday | 18 | 18. Object Detection | YOLOv3 and Keras | Understand model outputs and post-processing. | 60 | 45 | 45 | 30 | 180 | Inspect confidence, NMS and bounding boxes. | Not Started |  |  | 0%
2026-11-24 | Tuesday | 18 | 18. Object Detection | Custom object detection with Custom Vision | Prepare dataset, labels and train/validate. | 60 | 45 | 45 | 30 | 180 | Create a custom-detection project plan. | Not Started |  |  | 0%
2026-11-25 | Wednesday | 18 | 18. Object Detection | Exported model/inference + review | Deploy and test exported detection model. | 60 | 45 | 45 | 30 | 180 | Write object-detection evaluation summary. | Not Started |  |  | 0%
2026-11-26 | Thursday | 19 | 19. NLP with Deep Learning | Neural text preparation and word embeddings | Understand embedding spaces and semantic similarity. | 60 | 45 | 45 | 30 | 180 | Use pretrained or learned embeddings. | Not Started |  |  | 0%
2026-11-27 | Friday | 19 | 19. NLP with Deep Learning | Text classification with embeddings | Build embedding + dense sentiment model. | 60 | 45 | 45 | 30 | 180 | Train and compare against TF-IDF baseline. | Not Started |  |  | 0%
2026-11-28 | Saturday | 19 | 19. NLP with Deep Learning | TextVectorization | Automate vocabulary and token handling. | 60 | 45 | 45 | 30 | 180 | Build TextVectorization sentiment pipeline. | Not Started |  |  | 0%
2026-11-30 | Monday | 19 | 19. NLP with Deep Learning | Word order and RNNs | Understand sequence order, hidden state and limitations. | 60 | 45 | 45 | 30 | 180 | Train a simple RNN/LSTM text classifier. | Not Started |  |  | 0%
2026-12-01 | Tuesday | 19 | 19. NLP with Deep Learning | Pretrained NLP models | Use transformers for text classification. | 60 | 45 | 45 | 30 | 180 | Run pretrained text-classification pipeline. | Not Started |  |  | 0%
2026-12-02 | Wednesday | 19 | 19. NLP with Deep Learning | NLP revision + error analysis | Compare BoW/TF-IDF/RNN/transformer approaches. | 60 | 45 | 45 | 30 | 180 | Create model-selection table. | Not Started |  |  | 0%
2026-12-03 | Thursday | 20 | 20. NMT, Transformers & BERT | Neural machine translation; encoder-decoder | Understand source/target sequences and attention need. | 60 | 45 | 45 | 30 | 180 | Build translation data preprocessing pipeline. | Not Started |  |  | 0%
2026-12-04 | Friday | 20 | 20. NMT, Transformers & BERT | LSTM encoder-decoder | Understand sequence-to-sequence architecture. | 60 | 45 | 45 | 30 | 180 | Train or inspect a small LSTM NMT example. | Not Started |  |  | 0%
2026-12-05 | Saturday | 20 | 20. NMT, Transformers & BERT | Transformer encoder-decoders | Understand attention, positional encoding and parallelism. | 60 | 45 | 45 | 30 | 180 | Draw transformer NMT architecture. | Not Started |  |  | 0%
2026-12-07 | Monday | 20 | 20. NMT, Transformers & BERT | Transformer-based NMT model | Implement basic transformer components. | 60 | 45 | 45 | 30 | 180 | Run a compact transformer NMT notebook. | Not Started |  |  | 0%
2026-12-08 | Tuesday | 20 | 20. NMT, Transformers & BERT | Pretrained translation; BERT | Use pretrained translation and understand BERT encoder. | 60 | 45 | 45 | 30 | 180 | Compare translation outputs; inspect BERT embeddings. | Not Started |  |  | 0%
2026-12-09 | Wednesday | 20 | 20. NMT, Transformers & BERT | BERT QA + sentiment fine-tuning + review | Understand extractive QA and task adaptation. | 60 | 45 | 45 | 30 | 180 | Fine-tune a small BERT classifier or complete guided notebook. | Not Started |  |  | 0%
2026-12-10 | Thursday | 21 | 21. Azure Cognitive Services & Final Consolidation | Azure Cognitive Services overview; keys/endpoints | Understand managed AI services and authentication. | 60 | 45 | 45 | 30 | 180 | Create service selection matrix for business use cases. | Not Started |  |  | 0%
2026-12-11 | Friday | 21 | 21. Azure Cognitive Services & Final Consolidation | Calling APIs; containers | Use APIs securely and understand container option. | 60 | 45 | 45 | 30 | 180 | Design an API call flow with secrets handling. | Not Started |  |  | 0%
2026-12-12 | Saturday | 21 | 21. Azure Cognitive Services & Final Consolidation | Computer Vision Service | Use OCR/image analysis and assess outputs. | 60 | 45 | 45 | 30 | 180 | Run or simulate a Computer Vision workflow. | Not Started |  |  | 0%
2026-12-14 | Monday | 21 | 21. Azure Cognitive Services & Final Consolidation | Language, Translator and Speech Services | Map language, translation and speech APIs to tasks. | 60 | 45 | 45 | 30 | 180 | Create mini pipeline design for multilingual support. | Not Started |  |  | 0%
2026-12-15 | Tuesday | 21 | 21. Azure Cognitive Services & Final Consolidation | Contoso Travel integration case study | Compose multiple AI services in one application. | 60 | 45 | 45 | 30 | 180 | Create architecture diagram and user flow. | Not Started |  |  | 0%
2026-12-16 | Wednesday | 21 | 21. Azure Cognitive Services & Final Consolidation | Final revision & capstone presentation | Consolidate end-to-end ML/DL knowledge. | 60 | 45 | 45 | 30 | 180 | Present one project; complete final gap list and next-step plan. | Not Started |  |  | 0%
AI Foundry
CI/CD pipeliens and ci\cd regression tests
Formulas:
Date = [Date, row above]+IF(WEEKDAY([Date, row above],2)=6,2,1)

## way to prepare
Universal Interview Preparation Framework (Works for Any Technical Topic)
1. Definition (What?)
Goal: Explain the concept in 15–30 seconds.
Questions
What is it?
What category does it belong to?
What problem does it solve?
2. Motivation (Why?)
Understand why it exists.
Questions
Why was it introduced?
What problem did previous methods have?
What gap does it fill?
3. Working (How?)
Understand the complete workflow.
Questions
How does it work internally?
What are its components?
What happens step by step?
For algorithms:
Input → Processing → Output
For systems:
Client → API → Service → Database → Response
4. Core Components
Break the topic into pieces.
Questions
What are the main components?
Why does each exist?
What happens if one is removed?
5. Technical Terminology
List all important technical terms.
For each term answer
What is it?
Why is it needed?
Where is it used?
If you cannot explain a technical term simply, revisit it.
6. Mathematics / Theory (when applicable)
Don't memorize proofs.
Understand
Objective function
Loss function
Optimization
Equations
Complexity
Assumptions
For system topics, replace this with protocols, algorithms, or architectural principles.
7. Configuration / Hyperparameters
Questions
What can be configured?
What does each parameter control?
What happens if increased?
What happens if decreased?
For systems this becomes
Configuration settings
Scaling parameters
Resource limits
8. Strengths
Questions
Why is this technique popular?
Where does it perform well?
What advantages does it provide?
9. Weaknesses
Questions
When does it fail?
What are its limitations?
What assumptions can break?
Interviewers often focus here because it reveals depth of understanding.
10. Comparisons
Compare with similar concepts.
Questions
How is it different from alternatives?
When would you choose this?
When would you avoid it?
11. Practical Applications
Questions
Where is it used in industry?
Which companies use it?
How have you used it?
Always connect to one of your own projects if possible.
12. Production Perspective
Think like an engineer building real systems.
Questions
How is it deployed?
How is it monitored?
What can fail?
How is it scaled?
How is it secured?
This is where senior candidates distinguish themselves.
13. Failure Modes
Ask
"What can go wrong?"
Examples
Performance issues
Memory issues
Data issues
Incorrect predictions
Hallucinations
Latency
Drift
Race conditions
Network failures
Then know
Why it happens
How to detect it
How to mitigate it
14. Best Practices
Questions
What are recommended practices?
What mistakes do beginners make?
How do experts use it?
15. Interview Questions
Prepare
Basic
What is it?
Intermediate
How does it work?
Advanced
Why?
Expert
Trade-offs?
Architect
How would you design a production system using it?
16. Whiteboard Explanation
Finally ask yourself
Can I explain it on a whiteboard in five minutes?
Include
Architecture
Flow
Important equations
Components
Trade-offs
17. Design Trade-offs
For every topic, be able to answer:
Why would I choose this over another approach?
What am I sacrificing by choosing it?
How does it behave at scale?
What are the cost, latency, accuracy, and maintainability trade-offs?